## Instructions
Instructions for Completing the Grant Project Closeout Worksheet
Project accounting shall include all sources of revenues and project expenditures by budgeted expense category. The expense categories shall conform to the categories indicated in Appendix A and defined in Appendix E. Any change to the project budget or accounting must have been approved by both Recipient and the Department in an amendment to the project agreement. In the Project Agreement, the recipient agrees to provide an auditable accounting of expenditures of the project within 365 days of certification of beneficial occupancy and/or substantial completion. If approved by the department, this closeout worksheet can be accepted in lieu of an independent project audit that is otherwise required for projects receiving funding more than $300,000. Providing an accompanying excel file of the individual project transactions can assist department review. Additional transaction information and specific invoices may be requested before approval of the worksheet is granted by the department.
Project Information Tab
Information provided on the Project Information tab is used to populate fields on the Closeout Form worksheet and In-House Work Form worksheet. All requested information is contained in the Project Agreement between the Department of Education and Early Development and the Recipient.
Cost Categories and Budget information is located in Appendix A of the Project Agreement; review any project agreement amendment for changes to the project budget. Descriptions of approved expenditures for each cost category are found in Appendix E, with Chart of Accounts Function Codes (FC) (See also the Definitions tab).
Closeout Form
Under Revenues, identify all sources of project revenue, including grant amount and participating share. Other sources of revenue may include interest earned on grant payments, insurance proceeds, additional transfers from capital funds. The Total Revenue amount will show red until the value matches the Total Project amount on the Project Information tab.
Under Expenditures, list each vendor separately within a budgeted cost category. Note that no costs can be accounted for in project contingency.
Under Adjustments, If expenses were charged to the project that are non-allowable, (e.g., unapproved construction change orders, costs related to housing, construction management by consultant over the statutory limit), include a reason for the removal in the 'description' column and enter the amount in the 'expense' column. Under Adjustments, if revenues were received for the project from non-DEED grant sources (e.g., insurance proceeds, grants from other agencies, interest earnings, etc.) include a reason for the addtional revenue in the 'description' column and enter the amount in the 'revenue' column. These are funds that will be expended prior to grant and participating share amounts.
In-House Work Form
The In-house work form only needs to be included in the recipient requested and received approval to perform all or a portion of the project using recipient employees or materials. Identify individual employees and expenses by cost category, breaking out information by unit quantity and cost.
Definitions
Definitions of the cost categories are provided. Review expenditures to ensure conformation with the appropriate category.

## Project Information
Project Agreement Information
The inputs requested below populate information on the following Closeout and In-house Work Forms
School District | enter school district
School Name | enter school name
Project Name | enter project name
Project Number | enter project number
Review Project Agreement, Appendix A, "1. Project Scope of Work" to provide a brief summary of the Scope of Work, which follows lead-in phrase "a grant for the purpose of..." | installing/renovating a ....
From Project Agreement, Appendix A, "3. Project Funds", enter authority of grant appropriation (Chapter/SLA reference or Statute reference) | Chapter X/SLA XX, pageX, lines X-X OR AS 14.11.00X, 14.11.015, and 4 AAC 31
From Project Agreement, Appendix A, "4. Project Budget", as amended, enter project budget
Cost Category (Function Code) | Current Approved Budget Amount (as amended)
CM by Consultant (884) | 0
Land (882) | 0
Site Investigation (882) | 0
Design Services (883) | 0
Construction (885) | 0
Equipment / Technology (886) | 0
District Administrative Overhead / In-House CM (881) | 0
Percent for Art (888) | 0
Contingency (889) | 0
TOTAL Project | 0

## Closeout Form
Grant Closeout Worksheet In lieu of independent audit |  | Back Checks
School District: | enter school district | n/a
School Name: | enter school name | n/a
Project Name: | enter project name | n/a
Project Number: | enter project number | n/a
Revenues | n/a | n/a
Grant Amount: | 0 | #DIV/0!
Recipient Participating Share: | 0 | #DIV/0!
Interest on Grant Payments: | 0
Other Funds: | 0
Total Revenues: | 0 | 0
Expenditures | n/a
Construction Management by Consultant (FC 884) | Budget: $0,000
Vendor | Actual Expense
Subtotal CM by Consultant | 0 | #DIV/0!
Land (FC 882) | Budget: $0,000
Vendor | Actual Expense
Subtotal Land | 0
Site Investigation (FC 882) | Budget: $0,000
Vendor | Actual Expense
Subtotal Site Investigation | 0
Design Services (FC 883) | Budget: $0,000
Vendor | Actual Expense
Subtotal Design Services | 0
Construction (FC 885) | Budget: $0,000
Vendor | Actual Expense
Subtotal Construction | 0
Equipment / Technology (FC 886) | Budget: $0,000
Vendor | Actual Expense
Subtotal Equipment / Technology | 0
District Administrative Overhead / In-house CM (FC 881) | Budget: $0,000
Vendor | Actual Expense
Subtotal District Administrative Overhead | 0
Percent for Art (FC 888) | Budget: $0,000
Vendor | Actual Expense
Subtotal Percent for Art | 0
Project Contingency | Budget: $0,000
Total Project Budget | Budget: $0,000
Total Project Expenses | 0
Over (Under) Project Budget | 0
Adjustments | n/a
Expenses Not Reimbursable Under Grant
Description | Expense
Subtotal Non-reimbursable | 0
Revenue Expended Before Grant Funds
Description | Revenue
Subtotal Other Revenue | 0
Grant Payments
Total Reimbursable Grant Costs | 0
Over (Under) Grant Appropriation + Participating Share | 0
Total Reimbursable Grant Costs | 0
State Share | 0
Local Share | 0 | 0
Previous Grant Payments | 0
Final Grant Payment | 0
Total Grant Payment for enter project number | 0
Remaining Grant Balance to Return to Fund | 0
This is to certify that, for the purposes of compliance with a grant in the amount of $0,000.00, awarded under the authority of Chapter X/SLA XX, pageX, lines X-X OR AS 14.11.00X, 14.11.015, and 4 AAC 31 for the purpose of installing/renovating a ...., to the best of my knowledge, all funds were spent in a manner consistent with the language of the contract agreement with the State of Alaska, Department of Education & Early Development.
In addition, in lieu of an independent final project audit, I am providing the Department with an accounting of the project that includes a balance sheet listing all revenues and all expenditures by budget category for this project.
Signature of Grant Recipient | Date
Note on C7: state share
Note on C8: district share
Note on C11: project budget equal to revenue? More/less than?
Note on C17: Percentage compare percentage to max allowed under statute
Note on C74: Over (Under) district participating share

## In-house Work Form
In-House Work Form To Accompany Closeout Form Enter Expenses As Allowed By Department Approved In-House Request Begin entering approved in-house cost information in cell A8
School District: | enter school district
School Name: | enter school name
Project Name: | enter project name
Project Number: | enter project number
Site Investigation (FC 882) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
Subtotal Site Investigation | n/a | n/a | n/a | 0
Design Services (FC 883) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
Subtotal Design Services | n/a | n/a | n/a | 0
Construction (FC 885) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
0
Subtotal Construction | n/a | n/a | n/a | 0
Equipment / Technology (FC 886) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
Subtotal Equipment / Technology | n/a | n/a | n/a | 0
District Administrative Overhead (FC 881) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
Subtotal District Administrative Overhead | n/a | n/a | n/a | 0
In-house Construction Management (FC 881) | n/a |  |  | Budget: included with Dist. Admin.
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
Subtotal District Administrative Overhead | n/a | n/a | n/a | 0
Percent for Art (FC 888) | n/a | n/a |  | Budget: $0,000
Description List each expense or employee separately | Quantity | Unit | Unit Cost | Actual Expense
0
0
Subtotal Percent for Art | n/a | n/a | n/a | 0
In-House Project Total | n/a | n/a | n/a | 0
Signature of Grant Recipient |  |  |  | Date

## Definitions
Cost Category Definitions from Project Agreement
Construction Management by Consultant (FC 884)
Construction Management (CM) costs may include oversight of any phase of the project by a private contractor. Construction management includes management of the project's scope, schedule, quality, and budget during any phase of the planning, design and construction of the facility. Statutory Limit by Private Contractor: 2-4% [reference AS 14.11.020(c)]
Land (FC 882)
Land is a variable unrelated to construction cost and should include actual purchase price plus title insurance, fees and closing costs. Land cost is limited to the lesser of the appraised value of the land or the actual purchase price of the land. Land costs are excluded from project percent calculations.
Site Investigation (FC 882)
Site Investigation is also a variable unrelated to construction cost and should include land survey, preliminary soil testing, environmental and cultural survey costs, but not site preparation. Site investigation costs are excluded from project percent calculations.
Design Services (FC 883)
Design Services should include full standard architectural and engineering services and extra services such as educational specifications, condition surveys, construction administration, and post occupancy evaluation. Architectural and engineering fees can be budgeted based upon a percentage of construction costs. Because construction costs vary by region and size, so may the percentage fee to accomplish the same effort. Recommended: 6-10% (Renovation might run 2% higher)
Construction (FC 885)
Construction includes all contract work as well as force account for facility construction, site preparation and utilities. This is the base cost upon which others are estimated and equals 100%.
Equipment/Technology (FC 886)
Equipment/Technology includes all moveable furnishing, instructional devices or aids, electronic and mechanical equipment with associated software and peripherals (consultant services necessary to make equipment operational may also be included). It does not include installed equipment, nor consumable supplies, with the exception of the initial purchase of library books. Items purchased should meet the district definition of a fixed asset and be accounted for in an inventory control system. Equipment/Technology budgets have two benchmarks for standard funding: percentage of construction costs and per-student costs as discussed in DEED’s Guideline for School Equipment Purchases. If special technology plans call for higher levels of funding, itemized costs should be presented in the project budget separate from standard equipment. Recommended: 0-10% of construction cost or between $1700 - $3050 per student depending on school size and type.
District Administration Overhead / In-House CM (FC 881)
Overhead includes an allocable share of district overhead costs, such as payroll, accounts payable, procurement services, and preparation of the six-year capital improvement plan and specific project applications. The maximum for non-project specific indirect administrative costs is 3%, as defined in regulation [4 AAC 31.023(c)(7)] based on construction cost. It also includes In-House Construction Management (CM) which is similar to CM by Consultant, with the exception that in-house CM includes actual district/ borough staff time allocated to the project, staff travel expenses, and other direct costs of the in-house activity. The total of in-house construction management costs and construction management by consultant should not exceed 5% of the construction budget. Recommended: 2-9%
Percent for Art (FC 888)
Percent for Art includes the statutory allowance for art in public places. This may fund selection, design/fabrication, and installation of works of art. One percent of the construction budget is required except for REAA projects which require only one-half of one percent. The department recommends budgeting for art.
Contingency
Contingency is a safety factor to allow for unforeseen changes. This item is a project contingency for project changes and unanticipated costs in other budget areas, therefore no actual project cost can be attributed to contingency. Recommended: 5% Fixed
Project Total
The "Project Total Expenses" from the "Actual Expense" subtotals should equal all grants, participating share and other fund contributions to the project total. The "Total Project Budget" amount should reflect the amount listed in Appendix A of the Project Agreement.